EventPlanning.com

Event Planning Checklist

The master checklist, phase by phase. Works for weddings, corporate events, and parties.

Event: _______________________    Date: __________    Lead time: __________    Owner: _______________________

PHASE 1: FIRST DECISIONS (12 OR MORE WEEKS OUT)

| Done | Item | Notes |
| --- | --- | --- |
| ☐ | Define the goal and how you will know the event worked |  |
| ☐ | Set the budget ceiling and a 10 percent contingency |  |
| ☐ | Pick the date and a backup date |  |
| ☐ | Draft the guest list and estimate the count |  |
| ☐ | Shortlist 3 to 5 venues and request pricing |  |
| ☐ | Decide who owns which decisions (you, client, committee) |  |
| ☐ | Open a single tracking document for every decision and payment |  |

PHASE 2: BOOK THE BIG THINGS (8 TO 12 WEEKS OUT)

| Done | Item | Notes |
| --- | --- | --- |
| ☐ | Contract the venue and confirm what its fee includes |  |
| ☐ | Book catering and set the service style |  |
| ☐ | Book the key vendors: photo, music, rentals, florals as needed |  |
| ☐ | Get every vendor agreement in writing and signed |  |
| ☐ | Confirm insurance requirements with the venue |  |
| ☐ | Set the payment calendar for every deposit and balance |  |
| ☐ | Send save-the-dates if the event calls for them |  |

PHASE 3: DESIGN AND DETAILS (4 TO 8 WEEKS OUT)

| Done | Item | Notes |
| --- | --- | --- |
| ☐ | Lock the theme, decor plan, and color decisions |  |
| ☐ | Send invitations and set the RSVP deadline |  |
| ☐ | Finalize the menu and bar arrangement |  |
| ☐ | Plan audio visual: mics, speakers, screens, playlists |  |
| ☐ | Order rentals: tables, chairs, linens, extras |  |
| ☐ | Book staffing for setup, service, and teardown |  |
| ☐ | Confirm dietary restrictions and accessibility needs |  |

PHASE 4: LOCK IT DOWN (2 TO 4 WEEKS OUT)

| Done | Item | Notes |
| --- | --- | --- |
| ☐ | Give the venue the guest guarantee before the deadline |  |
| ☐ | Finish the seating plan |  |
| ☐ | Draft the run of show and circulate it for comments |  |
| ☐ | Reconfirm every vendor: arrival time, scope, contact |  |
| ☐ | Make final payments on schedule |  |
| ☐ | Build the day-of kit: tape, scissors, chargers, pens, meds |  |

PHASE 5: EVENT WEEK

| Done | Item | Notes |
| --- | --- | --- |
| ☐ | Confirmation call or text to every vendor |  |
| ☐ | Final guest count to catering |  |
| ☐ | Print the run of show and the contact sheet |  |
| ☐ | Walk the venue one final time |  |
| ☐ | Stage everything you are transporting yourself |  |

PHASE 6: EVENT DAY

| Done | Item | Notes |
| --- | --- | --- |
| ☐ | Arrive first, walk the space against the run of show |  |
| ☐ | Check in every vendor on arrival |  |
| ☐ | Run the day from the run of show, one owner per cue |  |
| ☐ | Capture photos of the setup before guests arrive |  |
| ☐ | Close out: teardown, load-out, venue walkthrough |  |

PHASE 7: THE WEEK AFTER

| Done | Item | Notes |
| --- | --- | --- |
| ☐ | Pay every remaining invoice |  |
| ☐ | Send thank-yous to client, vendors, and helpers |  |
| ☐ | Collect photos and add the best to your portfolio |  |
| ☐ | Ask for the review and one referral introduction |  |
| ☐ | Debrief: what drifted from plan, and fix the template |  |